## Sheet1
Group 41 - HertZone
Members | 2022-02-07 | 2022-02-08 | 2022-02-11 | 2022-02-14 | 2022-02-15 | 2022-02-19 | 2022-02-21 | 2022-02-22 | 2022-02-25 | 2022-02-28 | 2022-03-01
Adon
Create a gantt chart | bar: 2022-02-07 to 2022-02-08
Create a trello account | bar: 2022-02-11
Create a mindmap of initial ideas | bar: 2022-02-11 to 2022-02-14
Carry out research for Hertfordshire bot | bar: 2022-02-15 to 2022-02-22
Create a logo | bar: 2022-02-25
Assist with chatbot prototype | bar: 2022-02-28 to 2022-03-01
Alex
Create a trello account | bar: 2022-02-07
Familiarise self with HTML | bar: 2022-02-08 to 2022-02-11
Will carry out making wireframes for pc version | bar: 2022-02-11 to 2022-02-22
Finish Wireframes | bar: 2022-02-25
Assist with chatbot prototype | bar: 2022-02-28 to 2022-03-01
Anup
Create a trello account | bar: 2022-02-07
Will carry out research on topic | bar: 2022-02-08 to 2022-02-15
Find various articles related to crisis | bar: 2022-02-19 to 2022-02-21
Look into different crisis platform | bar: 2022-02-22 to 2022-02-25
Look into weather crisis and produce document | bar: 2022-02-28 to 2022-03-01
Mary
Create a trello account | bar: 2022-02-07
Find various articles related to crisis management | bar: 2022-02-08 to 2022-02-11
Create documents of research on crisis | bar: 2022-02-11 to 2022-02-21
Create a moodboard for design concepts | bar: 2022-02-22 to 2022-02-28
Submit all agenda meetings on trello | bar: 2022-03-01